NECONDE ENERGY LIMITED

ODIDI 11T

DRAFT HUD INVESTIGATION PROGRAM

OML 42

JUNE - 2015

APPROVALS

| ACTION | NAME | TITLE | SIGNATURE | DATE |
| --- | --- | --- | --- | --- |
| Prepared by | Oludewa Awani |  |  |  |
| Reviewed by |  |  |  |  |
| Agreed by |  |  |  |  |
| Approved by |  |  |  |  |

ODIDI-11T HUD INVESTIGATION PROGRAM

OBJECTIVES:

- To determine nature of HUD at 6978ftah

- To possibly retrieved suspected plug & prong at 6978ftah

COST & DURATION SUMMARY:

| Total Cost (MM$) | 64,290.00 |
| --- | --- |
| Total Duration (Days) | 2 |

N.B: Cost is based on CT & WL activity daily spread.

BASIC COMPLETION DATA:

| WELL | Tree Type | Tree Connection | Tubing Size | SCSSV Size/type | SCSSV Depth | Last survey/well entry |
| --- | --- | --- | --- | --- | --- | --- |
| Odidi 11T | Cooper Cameron ‘FC’ | 3-1/2” ACME | 3-1/2” 9.3Ib/ft. Drift 2.73’’ | 3” OB-6 ScSSSV | 149’ | Retrieved 3” x 2 7/8” OB-6 RIH 1.80” G/C Drift to 6978ft, H/Up. POOH. Flow tested from 1200psi to 1000psi. Gas only |

NB:

- Ensure well site visit is carried out to confirm X-mas tree adaptor prior to mob

- Conduct a well-slot visit to ensure that the well-slot is accessible for WL operation before mobilization of WL unit to site.

- Ensure completion of FLM and SLM works on wellhead, before commencement of WL operation.

PRODUCTION DATA & WELL STATUS:

| Test Date | Gross | Net Oil | BSW | GOR | THP | Bean | Present Well Status |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | bbl/d | bopd | % | scf/bbl | psig | x/64" |  |
| 01/02/2006 | 1446 | 1013 | 30 | 378 | 405 | 28 | C/I |

(DFE to top CHH) is 34ft

SAND: D3.0E

KNOWN WELL PROBLEM: HUD @ 6778ftAH during 2014 wireline re-entry

See Appendix B attached (well completion schematics).

#### ROLES & RESPONSIBILITIES:

Field Engineer:

The Field Engineer is in charge of the job at the location. He should hold pre-job safety briefing and job safety analysis (JSA), issue all safety permits and has overall responsibility for all safety matters during the operation. He should submit daily progress report to the line-manager/Supervisor.

Production Supervisor:

Operate (or assign an operator to operate) the wellhead control units and tree valves at the request of the Field Engineer. He should provide directives based on standard procedure at the wellhead and or flowstation.

Production Operators:

Responsible for wellhead operations, opening and closing of wellhead valves

CT/WL Contractor

Supply certified CT/WL crew, CT/WL equipment, tools and performs operations in a safe and professional manner.

CT/WL Operator

Run CT unit, auxiliary equipment and perform operations as required, in a safe manner.

To submit a detailed report at end of exercise

NB: Invoice to be submitted along with the comprehensive CT/WL summary reports.

SAFETY & IMPORTANT NOTE

- Hold tool box meeting and job safety analysis (JSA) onsite with wire line contractor and crew prior to commencement of job.

- General safety practices in well intervention to apply during the job.

- All pressure equipment (chicksans, Xmas tree adapter, wire line lubricator, wireline BOP etc) must have valid test certificate and/or test bands indicating test pressures/dates.

- NO SMOKING rule MUST be strictly enforced.

- Unauthorized person(s) must not be allowed on/around the location during the job.

- All personnel must wear appropriate personal protective equipment (PPE) which includes safety shoes, hard hat, floating device, coverall, eye-google, hand-gloves, nose mask etc.

- Carry out well head gas test using a portable gas tester prior to commencement of well entry and during swabbing activity.

- Ensure zero environmental pollution.

- All work should be carried-out during daylight. Work should not progress under poor visibility or bad weather condition.

- Ensure the use of correct tools and equipment during the job.

- Leaks should be avoided by ensuring that the lubricator is not leaking.

EQUIPMENT REQUIRED

These may include, but not limited to the following;

- W/L unit / tools and surface equipment.

- Various sizes of gauge cutters (1.86’’, 2.25’’, 2.73’’ for full bore drift)

- GS pulling tool with EQ prong + contingency plug retrieving tools

FRONT-END ACTIVITIES

- Validate premob certificate of CT/WL equipment and tools.

- Ensure all safety and environmental precautions have been observed

- Check and confirm that production operation is fully aware of the intended operation

- Check and record well head pressures before commencement of job.

- Check wellhead for integrity, check and confirm the position of the valves, ensure xmas tree valves are closed, read and record CITHP, bleed off CITHP.

- Ensure flowback tank has a flame arrestor installed in the vent stack and all hoses and lines between the flow-back tank and wellhead are in good conditions and correct pressure rating.

WIRE-LINE ACTIVITIES

- Check and confirm that the well is closed-in.

- Record initial wellhead pressures (CITHP, CHP) using the provided template (If casing head    pressure is high, bleed off, if it rises again, report to the Field Engineer or the office).

- Rig up Wire line BOP and lubricator on wellhead and pressure test to the CITHP for 15 minutes.

- Hook up wing arm (flow) to swab tank (environmental barge).

- M/U 2.73” GC on wireline and RIH to 149ftah to confirm whether SCSSSV is in place, if in place, RIH GS pulling tool with EQ prong to retrieve ScSSSV and POOH

- M/U 1.86’’ GC on slickline and drift to HUD at 6978ftah and POOH. (If other HUD is encountered before 6978ftah, run an LIB to investigate nature of HUD, Monitor drag every 500ft, if drag exceeds 500 lb review with Field Engineer. Monitor pulling weight when POOH)

- M/U 1.86’’ LIB and RIH on slickline to investigate nature of HUD at 6978ftah and POOH. (Monitor drag every 500ft, if drag exceeds 500 lb review with Field Engineer, monitor pulling weight when POOH). If HUD is plug & prong, proceed to the next item, Otherwise contact the office for advise.

- M/U and RIH pulling tool, retrieve suspected plug and prong at 6978ftah and POOH. (Monitor drag every 500ft, if drag exceeds 500 lb review with Field Engineer, monitor pulling weight when POOH).

- M/U running tool with prong and install ScSSSV at 149ftah. Leak test ScSSSV by venting off pressure at surface

- Perform an inflow test to environmental barge to ascertain that zone is capable of production.

- RIH and install 3’’ NRV inside the tubing hanger and leak test okay.

- Shut-in the well by closing the xmas tree valves and rig down wireline lubricator.

- Record final wellhead pressures (CITHP, CHP) using the provided template.

- Demobilize from wellhead.

APPENDIX A: Wellhead Pressure Recording Template

Well Name:  Odidi-11T

| Initial Recording | On Arrival |
| --- | --- |
| Date: | Time: |
| CITHP (psig): | CHP (psig): |
| Final Recording | Before Departure |
| Date: | Time: |
| CITHP (psig): | CHP (psig): |
| SEE TABLE BELOW FOR CORRECT DRIFT SIZE SELECTION: Tbg Size; 2-3/8”; 2-7/8”; 3-1/2”; 4-1/2”. Drift Size; 1.86”; 2.25”; 2.73”; 3.75”. |

APPENDIX B: Odidi-11 Completion Schematic