NECONDE ENERGY LIMITED

ODIDI-30S

DRAFT: WELL KILL & XMAS TREE CHANGE OUT PROGRAM

OML 42

JUNE 2015

APPROVALS

| ACTION | NAME | TITLE | SIGNATURE | DATE |
| --- | --- | --- | --- | --- |
| Prepared by |  |  |  |  |
| Reviewed by |  |  |  |  |
| Agreed by |  |  |  |  |
| Approved by |  |  |  |  |

ODIDI-30S WELL KILL & XMAS TREE/MASTER VALVE CHANGE-OUT PROGRAM

OBJECTIVES:

- Kill well

- Retrieve stuck ScSSSV across master valve

- Replace Xmas tree

- Flush control line with appropriate fluid

- Secure well

COST & DURATION SUMMARY:

| Total Cost (MM$) | 558,231.00 |
| --- | --- |
| Total Duration (Days) | 3 |

N.B: Cost is based on CT & WL activity daily spread.

BASIC COMPLETION DATA:

| WELL | Tree type | Tree Connection | Tubing Size | SCSSV Size/type | SCSSV Depth | Last Re-entry |
| --- | --- | --- | --- | --- | --- | --- |
| Odidi 030S | Cooper Cameron ‘FC’ | 2-3/8” ACME | 2-3/8" 4.7Ib/ft Drift 1.86’’ | n/a | n/a | 2010: MV stiff, suspect ScSSV across tree. Attempted to flush Ctrl Line but BU to 4Kpsi with 3-4 pump strokes |

NB:

- Ensure well site visit is carried out to confirm X-mas tree adaptor prior to mobilization

- Conduct a well-slot visit to ensure that the well-slot is accessible for CTU operation before mobilization of CTU to site.

- Ensure completion of FLM and SLM works on wellhead, before commencement of CTU operation.

(DFE to top CHH is 32.20ft)

SAND: D3000E

MID PERF: 7012 ftah

Datum Depth:6950 TVDss

Proposed Killing depth is: 7012 ftah.

Last know FTHP: 300psi

Last known Oil production rate: 700bopd (05/24)

Known well Problem(s):

Master valve stuck in half open position with ScSSSV suspected to be across it.

SCSSSV control line is blocked. Xmas tree cavities damaged.

No NRV or plug installed.

See Appendix B attached (well completion schematics).

PRODUCTION DATA:

| Test Date | Gross | Net Oil | BSW | GOR | THP | Bean |
| --- | --- | --- | --- | --- | --- | --- |
|  | bbl/d | bopd | % | Mscf/bbl | psig | /64" |
| 13/03/2004 | 1213 | 910 | 25 | 0.45 | 300 | 44 |

ROLES & RESPONSIBILITIES:

Field Engineer:

The Field Engineer is in charge of the job at the location. He should hold pre-job safety briefing and job safety analysis (JSA), issue all safety permits and has overall responsibility for all safety matters during the operation. He should submit daily progress report to the managers.

Production Supervisor:

Operate (or assign an operator to operate) the surface control unit and tree valves at the request of the Field Engineer.

Wireline Operator:

Perform operations in a safe and professional manner in accordance to the program and Field Engineer instructions.

Wireline Contractor:

To submit a detailed report at end of the well securing exercise

NB: Invoice to be submitted along with the comprehensive wireline and summary reports.

SAFETY & IMPORTANT NOTE

- Hold tool box meeting and job safety analysis (JSA) onsite with wire line & well securing contractor and crew prior to commencement of job.

- General safety practices in well intervention to apply during the job.

- All pressure equipment (chicksans, Xmas tree adapter, wire line lubricator, wireline BOP etc) must have valid test certificate and/or test bands indicating test pressures/dates.

- NO SMOKING rule MUST be strictly enforced.

- Barriers and warning signs should be erected all non-essential personnel to stay clear of the area. Unauthorized person(s) must not be allowed on/around the location during the job.

- All personnel must wear appropriate personal protective equipment (PPE) which includes safety shoes, hard hat, floating device, coverall, eye-google, hand-gloves etc.

- Carry out well head gas test using a portable gas tester prior to commencement of well entry.

- No environmental pollution.

- All work should be carried-out during daylight. Work should not progress under poor visibility or bad weather condition.

- Ensure the use of correct and certified tools and equipment during the job.

- Leaks should be avoided by ensuring that the lubricator is not leaking.

- Carry out visual wellhead inspection and assessment prior to commencement of work

- Inspect and assess xmas tree valves, certify okay before commencement of work

- All equipment must be positioned at least 50ft away from the wellhead.

- All equipment must be fitted with spark arrestors

- Where applicable, gas monitors should be available and located in appropriate detection areas.

- Radio handsets should be utilized to maintain communication during the job.

EQUIPMENT REQUIRED:

- W/L unit, tools and surface equipment.

- Various sizes of gauge cutters (1.86’’. 2.25’’, 2.73’’, 3.75’’ for full bore drift)

- Correctly sized GS/SB pulling tool with EQ prongs plus contingency for retrieving PXN/PX plugs and prongs

- Correctly sized SB & X-Line running tools for installing PXN/PX plugs and prongs

- Correctly sized NRV’s, VR plugs, PXN plugs with prongs for temporary well securing

WELLHEAD UPFRONT ACTIVITIES

- Carry out visual wellhead inspection and assessment prior to commencement of work

- Inspect and assess xmas tree valves, certify okay before commencement of work

- Check and confirm the position of the xmas tree valves

- Validate premob certificate of equipment.

- All safety and environmental precautions should be observed

WIRELINE ACTIVITIES – LONG STRING (ODIDI-30L) SECURING

  - Record well head CITHP with calibrated pressure gauge of appropriate range.

  - Leak test and confirm xmas tree valve integrity.

  - R/U standard wellhead lubricator, pressure test lubricator with CITHP for 15mins

  - RIH 2’’ PX plug with prong and install in XEL nipple at 158ftah, leak test okay.

  - Install NRV in tubing hanger, leak test and POOH.

  - R/D lubricator.

  - Close all xmas tree valves

PUMPING / KILL ACTIVITIES USING THE WING VALVE – SHORT STRING (ODIDI-30S)

- Check and record well head pressures

- Rig up pumping lines to Odid 030S wing/swab valve and pressure test surface lines to 3000 psi for 15 mins.

- Kill well by bull heading with 37barrels of filtered inhibited brine (density of 8.8ppg) without exceeding surface pumping pressure of 1000psi

- Monitor well for 2hrs.

- If well is not stable spot 4bbl of LCM pill across the D3000E sand.

- If well is stable after 2hrs, proceed with fishing of SCSSSV.

CONTINGENCY FOR KILLING SHORT STRING: D3.0E SAND (ODIDI-30S)

Secure the long string by installing 2’’ plug with prong in SSD/sleeve at 7046ftah, leak test okay.

      - Record well head CITHP with calibrated pressure gauge of appropriate range.

      - Leak test and confirm xmas tree valve integrity.

      - R/U standard wellhead lubricator, pressure test lubricator with CITHP for 15mins

      - RIH 2’’ PX plug with prong and install in SSD at 7046ftah, leak test okay.

      - RIH shifting tool and open SSD at 6967ftah and POOH

      - Kill short string by bullheading thru the long string SSD into the D3.0E sand. Bullhead with 37barrels of filtered inhibited brine (density of 8.8ppg) without exceeding surface pumping pressure of 1000psi

      - Stop bullheading after pumping 37bbls of 8.8ppg inhibited brine, Monitor well for 2hrs, by observing for returns thru the short string

      - If well is not stable, spot 4bbl of LCM pill across the D3000E sand, thru the long string SSD.

      - If well is stable after 2hrs, proceed with fishing of SCSSSV.

      - R/D lubricator.

      - Close all xmas tree valves

SCSSSV FISHING ACTIVITIES (ODIDI-30S)

- Record well head CITHP with calibrated pressure gauge of appropriate range

- R/U lubricator and pressure test to well CITHP for 15 minutes

- RIH LIB and confirm SCSSSV across master valve (if present, go to 4)

- RIH appropriate tool and retrieve SCSSSV across master valve

XMAS TREE REPLACEMENT

- Replace Xmas tree with new tree assembly. Retain the kill line during repair of the master valve for immediate re-kill if well comes alive.

WIRE LINE ACTIVITIES/TEMPORARY WELL SECURING

- R/U Wire line lubricator and pressure test to CITHP.

- RIH 1.86” GC tool and drift to separation tool at 6969ftah and POOH

- RIH and install 2’’ plug with prong at XEL nipple at 125ftah, leak test okay.

- Flush control line free of obstruction with appropriate fluid.

- POOH and R/D

APPENDIX A: Wellhead Pressure Recording Template

Well Name:  Odidi-030S

| Initial Recording | On Arrival |
| --- | --- |
| Date: | Time: |
| CITHP (psig): | CHP (psig): |
| Final Recording | Before Departure |
| Date: | Time: |
| CITHP (psig): | CHP (psig): |
| See table below for correct drift size selection: Tbg Size; 2-3/8”; 2-7/8”; 3-1/2”; 4-1/2”. Drift Size; 1.86”; 2.25”; 2.73”; 3.75”. |

APPENDIX D: Odidi-030 Completion Diagram