ODIDI 47T

UNPLUGGING, TR-ScSSSV LOCKOUT AND PB VALVE INSTALLATION PROGRAM (DRAFT)

OML 42

JUNE 2015

APPROVALS

| ACTION | NAME | TITLE | SIGNATURE | DATE |
| --- | --- | --- | --- | --- |
| Prepared by | Amusa Ademola | Snr PE |  |  |
| Agreed by | Oludewa Awani |  |  |  |
| Reviewed by |  |  |  |  |
| Approved by |  |  |  |  |

UNPLUGGING, TR-ScSSSV LOCKOUT AND PB VALVE INSTALLATION PROGRAM

OBJECTIVES

- Unplug the interval by retrieving NRV in the tubing hanger and the plug/prong inside the tubing at TRScSSSV depth

- Carry out drift-run to establish the tubing is free

- Carryout inflow test of the interval

- Run Schlumberger flow exercise tool to confirm TR-ScSSSV is permanently opened

- Insert PB Valve and temporarily secure the well with NRV

COST & DURATION SUMMARY:

| Total Cost (MM$) | 64,290.00 |
| --- | --- |
| Total Duration (Days) | 2 |

N.B: Cost is based on CT & WL activity daily spread

WORK BACKGROUND

The TRScSSSV was stucked in open position, this rendered the well unsafe for production. The well was plugged off for safety reason in 2004. Tubing valve insert was proposed by the former operator. Attempts to open TR-ScSSSV in 2014 was unsuccessful because there is a suspected plug in the TR-ScSSSV depth. The plug must be removed and PB valve inserted.

BASIC COMPLETION DATA:

| Well | Tree Type | Tree Conn | Tubing Size | Min. ID Tbg Sub-Assy | ScSSSV Size/type | ScSSSV Depth | Last survey/well entry |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Odidi 47T | Vetco Gray VG-200 | 3-1/2’’ ACME | 3-1/2’’ 9.3Ib/ft Drift 2.73’’ | 2.635’’@XN-nipple | 3-1/2’’ HCS Camco TRDP-4E-ScSSV | 133” | 2004 |

- NB: Ensure well site visit is carried out to confirm X-mas tree adaptor prior to mob

- Conduct a well-slot visit to ensure that the well-slot is accessible for WL operation before mobilization of WL unit to site.

- Ensure completion of FLM and SLM works on wellhead, before commencement of WL operation.

LAST PRODUCTION:

| Date | Gross (BLPD) | Bean x/64” | THP (Psig) | BSW (%) | GOR (SCF/B) |
| --- | --- | --- | --- | --- | --- |
| 26/12/2003 | 2787 | 32 | 285 | 69 | 482 |

DFE to Top TBG Head Spool: 34.40 ft

SAND: E5.0X

KNOWN WELL PROBLEM(S): HBSW

Refer appendix-B below for well completion schematics.

#### ROLES & RESPONSIBILITIES:

Field Engineer:

The Field Engineer is in charge of the job at the location. He should hold pre-job safety briefing and job safety analysis (JSA), issue all safety permits and has overall responsibility for all safety matters during the operation. He should submit daily progress report to the manager.

Production Supervisor:

Operate (or assign an operator to operate) the wellhead control unit and tree valves at the request of the Field Engineer. He should provide directives based on standard procedure at the wellhead and or flowstation.

Production Operators:

Responsible for wellhead operations, wellhead control unit, opening and closing of wellhead valves.

Wireline Contractor:

Supply wireline crew and perform operations in a safe and professional manner.

Wireline operator:

To submit a detailed report at end of exercise

NB:

Invoice to be submitted along with the comprehensive wireline and summary reports.

#### SAFETY & IMPORTANT NOTE

- Hold tool box meeting and job safety analysis (JSA) onsite with wire line contractor and crew prior to commencement of job.

- General safety practices in well intervention to apply during the job.

- All pressure equipment (chicksans, Xmas tree adapter, wire line lubricator, wireline BOP etc) must have valid test certificate and/or test bands indicating test pressures/dates.

- NO SMOKING rule MUST be strictly enforced.

- Unauthorized person(s) must not be allowed on/around the location during the job.

- All personnel must wear appropriate personal protective equipment (PPE) which includes safety shoes, hard hat, floating device, coverall, eye-google, hand-gloves, nose mask etc.

- Carry out well head gas test using a portable gas tester prior to commencement of well entry and during swabbing activity.

- Ensure zero environmental pollution.

- All work should be carried-out during daylight. Work should not progress under poor visibility or bad weather condition.

- Ensure the use of correct tools and equipment during the job.

- Leaks should be avoided by ensuring that the lubricator is not leaking.

EQUIPMENT REQUIRED

These may include, but not limited to the following;

- W/L unit / tools and surface equipment.

- Various sizes of gauge cutters (1.86’’, 2.25’’, 2.73’’  for full bore drift)

- Flow exercise tool for confirming TR-ScSSSV lock-out

- Newly calibrated 3’’ PB Valve and 3’’ NRV’s

IMPORTANT ONSITE CHECKS BEFORE COMMENCEMENT OF ACTIVITIES

- Validate premob certificate of WL equipment and tools.

- Ensure surface acquisition system is working

- Ensure all safety and environmental precautions have been observed

- Check and confirm the position of the valves

- Check and confirm that production operation is fully aware of the intended operation

OPERATIONS:

Well Head Upfront Activities

Zero all measurement at CHH

1. Record well head pressures (CITHP & CHP) with calibrated pressure gauge of appropriate range.

2. Leak test and confirm Xmas tree valve integrity (if ok proceed to item 3)

3. R/U standard well head lubricator and pressure test to well CITHP for 15 minutes

4. RIH and retrieve 3” NRV from tubing Hanger.

5. R/D wellhead standard lubricator and record CITHP

WIRE LINE ACTIVITIES:

    - Check and confirm that the well is closed-in.

    - Record wellhead pressures (CITHP, CHP) using the provided template (If casing head pressure is high, bleed off, if it rises again, report to the Field Engineer or Office).

    - Rig up wire line BOP and lubricator on wellhead and pressure test to the CITHP for 15 minutes.

    - Hook up wing valve flow arm to the swab tank (environmental barge).

    - M/U 2.73” GC on WL toolstring and RIH to 133ftah (TR-ScSSSV depth) to confirm free tubing bore to TR-ScSSSV depth (If any HUD is encountered, run an LIB and report findings to the office).

    - RIH an LIB to 133ftah (TR-ScSSV depth) to confirm nature/profile of suspected plug and POOH.

    - RIH GS pulling tool (or appropriate pulling tool), equalize pressure and retrieve plug at 133ftah. Record pulling weight.

    - Make a drift run using 2.73’’ GC tool to XN Nipple depth of 6000ftah and POOH. If any HUD is encountered, run an LIB and report findings to the office for advice, Check for drag every 500ft, if drag exceeds 500 lb, review job with Field Engineer.

    - Perform inflow test to environmental barge to ascertain that zone is capable of production.

    - M/U and RIH Schlumberger Flow Exercise tool to TR-ScSSSV depth, confirm valve is permanently opened. Otherwise permanently lock-open TR-ScSSV and POOH.

    - M/U PB valve and equalizing sub on wireline, RIH and set valve at 133ftah. (Note: Set valve closing pressure at 80psi)

    - Leak test the PB Valve as per standard procedure, if okay POOH.

    - RIH and install 3’’ NRV in tubing hanger and POOH.

    - Shut-in the well and rig down wireline lubricator.

    - Record final wellhead pressures (CITHP, CHP) using the provided template.

WELL NAME:  Odidi 047T

| Initial Recording | On Arrival |  |  |
| --- | --- | --- | --- |
| Date: | Time: |  |  |
| CITHP (psig): | CHP (psig): |  |  |
| Final Recording | Before Departure |  |  |
| Date: | Time: |  |  |
| CITHP (psig): | CHP (psig): |  |  |
| SEE TABLE BELOW FOR CORRECT DRIFT SIZE SELECTION: Tbg Size; 2-3/8”; 2-7/8”; 3-1/2”; 4-1/2”. Drift Size; 1.86”; 2.25”; 2.73”; 3.75”. |

APPENDIX A: ODIDI 047T COMPLETION DIAGRAM